## Project planning
PROJECT PLANNING EXAMPLE
This example accompanies the Step-by-step plan project planning on BeroepKunstenaar.nl.
Go to Step-by step plan project planning
View the other tabs for completed examples of the planning of an exhibition and the planning of a production for a season.
Planning Form, to be filled in by yourself
Date: | … … …
Project name: | … … …
Phase | Activity | By | During the months
|  |  | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
Research |  | X
Development Phase | 1 | X and Y
| 2 | etc.
3
4
Production Phase | 1
2
3
4
Follow-up
Use lines or coloured bars to mark the duration (completion time) of a certain activity.
You can use dotted lines to link activities to each other.
The lines below are examples. You can shorten or lengthen them, or make them straight or diagonal. You can also make lines using the Drawing toolbar.
Bar for completion times:
Connecting line:
This form and the accompanying step-by-step plan have been adapted from a chapter in the book:
Projectmanagement 1, Een professionele aanpak van evenementen, by J. Verhaar, Boom, ISBN 90-5352-6358

## Example exhibition
Example of planning exhibition
planning created: 9 May 2022
Projectname | exhibition in gallerie X
Opening | 5 May 2024
Phase | activity | by | during the months
|  |  | Jan | Feb | March | April | May | June | July | Aug
Preparation | preparation exhibition | artist
| publicity material | galleryowner
25
| mailinglist | artist | during the months March: 25
| planning | artist
budget
Opening | catering | galleryowner | during the months May: 5
| music | artist
Exhibition period
[7 empty] | 5 | 25
Evaluation |  | artist / galleryowner

## Example performance
Example of a seasonalplanning for performances
Date | 9 May 2022
year | 2023 | [16 empty] | 2024
month | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June
week | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Activity
Production A
rehearsels
try-outs
premiere | [9 empty] | 3e
performances
Production B
rehearsels
try-outs
premiere | [25 empty] | 25e
performances